Project planner uses periods for intervals. Start=1 is period 1 and duration=5 means project spans 5 periods starting from start period. Enter data starting in B5 to update the chart
Enter a period in the range of 1 to 60 or select a period from the list. Press ALT+DOWN ARROW to navigate the list, then ENTER to select a value
Type a value from 1 to 60 or select a period from the list-press CANCEL, ALT+DOWN ARROW, then ENTER to select a value
This legend cell indicates plan duration
This legend cell indicates actual duration
This legend cell indicates the percentage of project completed
This legend cell indicates actual duration beyond plan
This legend cell indicates the percentage of project completed beyond plan
Periods are charted from 1 to 60 starting from cell H4 to cell BO4
Enter activity in column B, starting with cell B5

Enter plan start period in column C, starting with cell C5
Enter plan duration period in column D, starting with cell D5
Enter actual start period in column E, starting with cell E5
Enter actual duration period in column F, starting with cell F5
Enter the percentage of project completed in column G, starting with cell G5
Title of the project. Enter a new title in this cell. Highlight a period in H2. Chart legend is in J2 to AI2
Select a period to highlight in H2. A Chart legend is in J2 to AI2
## March
Social Pulse Insight Hub
Date: March 2024					Period Highlight:	1			Plan Duration					Actual Start					% Complete					Actual					% Complete
ACTIVITY	PLAN START	PLAN DURATION	ACTUAL START	ACTUAL DURATION	PERCENT COMPLETE	PERIODS
					1	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31
Initiation	1	14	1	15	100%
Planning	3	7	15	1	100%
Design	15	2	15	0	35%
Mockups	15	2	15	0	10%
Database	16	2	0	0	85%
Development	16	10	0	0	85%
Env. Setup	16	2	0	0	50%
Backend	17	4	0	0	60%
Frontend	19	4	0	0	75%
Testing	16	14	0	0	100%
Test Plan	16	14	0	0	60%
Bug Fixing	20	10	0	0	0%
Presentation	28	4	0	0	50%
Preparation	28	3	0	0	0%
Delivery	30	2	0	0	1%